COMPLETED WEEK 6 RESPONSE – DATA ANALYTICS TRACK

HealthConnect Clinic Experience Lab
Project: Improving Patient Appointment Attendance and Healthcare Support Using Data and AI
Week 6 | Data Analytics

SECTION 1 — TRACK & WEEK 6 POSITION

1. Track Information

Track: Data Analytics
Track Lead / Role: Data Analytics learner/analyst
Other Contributors: None identified for Week 6 cross-track work
Date of Update: 14 September 2026

2. Week 5 Starting Position

Main output/artefact: HealthConnect appointment analytics Power BI dashboard with KPIs, visual analysis, insights and recommendations.
Key finding/result: No-show behaviour was associated with booking lead time, previous no-show history, distance to clinic and reminder status.
Main limitation/unresolved issue: The analysis was observational and could not establish causation; some variables contained missing values.
Dependencies carried into Week 6: Deepen important findings, validate KPIs, improve decision support and prepare for Week 7 without repeating the Week 5 EDA.

3. Week 6 Expected Position

Develop advanced/decision-support analysis from Week 5; validate important KPIs and findings; conduct deeper segmentation and cross-variable analysis; produce evidence-based recommendations; document limitations; prepare an analytical output that could support Data Science; and prepare Week 7 testing requirements.

4. Current Week 6 Position

☒ Substantially Complete
The core Week 6 analytical work is complete. Cross-track integration with Data Science is NOT complete because no available Data Scientist/receiving track was identified. It is therefore recorded as pending rather than claimed as completed.

SECTION 2 — WEEK 6 PROGRESS & CHANGE

5. What did your track actually complete during Week 6?

Completed: deeper analysis of booking lead time, previous no-show history, distance and reminder status; reminder × lead-time analysis; KPI consistency validation; identification of high-risk segments; decision-support recommendations; dashboard improvement; limitations documentation; candidate-feature handoff content for Data Science; and Week 7 testing preparation.

6. What materially improved from the Week 5 position?

Week 5: Initial EDA and individual relationships were presented in the dashboard.
Week 6: The work was extended into cross-segment comparisons and decision support. Reminder status was examined within lead-time groups; high-risk patterns were prioritised; KPIs were checked for internal consistency; and findings were translated into operational recommendations.
Reason: Week 6 required deeper development rather than repetition of Week 5.

7. What remains incomplete?

Activity: Actual cross-track integration with Data Science.
Status: Pending / Not Yet Completed.
Reason: I could not identify an available Data Scientist/receiving track.
Dependency/blocker: Data Science counterpart availability.
Next action: Complete the analytical handoff/review when a Data Science counterpart becomes available.
Person/track required: Data Science / ML counterpart.

SECTION 3 — CROSS-TRACK INTEGRATION

8. Which other track(s) did your work connect with during Week 6?

☒ No cross-track connection yet.
The intended connection was Data Analytics → Data Science, but actual integration did not occur.

9. What did your track require from each relevant track?

Data Science was the intended receiving track. Required input/output: review and potential use of analytical findings/candidate variables for no-show prediction. Why needed: to assess whether the strongest analytical variables are useful in predictive modelling. Status: Pending.

10. What did your track provide to another track?

Prepared analytical findings and candidate variables: booking lead time, previous no-shows, distance to clinic and reminder status. Purpose: inform potential no-show prediction modelling. Status: Prepared, but not handed over/integrated because no receiving Data Science counterpart was available.

11. What actually happened at the integration point?

No actual cross-track integration occurred. The analytical output was prepared with Data Science use in mind, but communication, handoff and integration are not being reported as completed because there was no available receiving Data Scientist.

12. Integration Outcome

☒ Integration planned but not yet started
Explain: The analytical output is prepared for a potential handoff, but there is no evidence of incorporation into another track's model, pipeline or artefact.

13. What changed because of the integration?

Before integration: No downstream Data Science model/feature change existed.
After integration: No downstream change occurred because integration did not take place.
Resulting change: The Analytics output was strengthened and prepared for future integration, but no confirmed cross-track workstream change occurred.

14. What evidence demonstrates that the integration actually occurred?

☒ Not yet integrated.
There is evidence of the analytical work itself, but no downstream artefact, model change, joint output or review record proving actual integration.

SECTION 4 — HANDOFF, DEPENDENCY & READINESS CONTROL

15. What dependencies currently affect your track?

Dependency: Data Science counterpart availability.
Required input/output: Review and potential incorporation of analytics findings into predictive modelling.
Status: Pending.
Impact if delayed: Cross-track integration and downstream feature validation remain incomplete.

16. Are you currently waiting for another track?

☒ Yes
Track: Data Science
Required input/output: Receiving-track review/use of candidate features and findings.
Why needed: Complete intended integration and downstream validation.
Activity affected: Cross-track handoff and predictive-model feature validation.
Current status: Pending.

17. Is another track currently waiting for your output?

☒ No confirmed receiving track at present. The analytics output has been prepared for potential Data Science use, but no actual receiving-track handoff has occurred.

18. Has any dependency changed since Week 5?

☒ Yes.
Previous position: Data Science integration was an intended next step.
Current position: Integration remains pending because an available receiving counterpart could not be identified.
Impact: No downstream model/feature change can be evidenced.
PM action: Establish a named Data Science integration point.

SECTION 5 — OUTPUT READINESS & VALIDATION

19. Is your current output ready for downstream use?

☒ Conditionally Ready
The analytical findings are prepared, but downstream use should follow Data Science review, feature validation, missing-value review and leakage checks.

20. What must be true before another track can safely/usefully consume your output?

1. Receiving team reviews analytical definitions and KPI calculations.
2. Candidate variables are checked for leakage, missingness and modelling suitability.
3. Findings are understood as associations, not proven causal effects.

21. Does your output require validation, review, or approval from another track?

☒ Yes
Validator: Data Science / ML counterpart.
Needs validation: candidate feature usefulness, leakage risk, missing-value treatment and predictive performance.
Status: Not yet started.

22. What is the current status of your output?

☒ Produced
☒ Conditionally ready
☒ Ready for Week 7 analytical testing preparation
Evidence: Week 6 advanced analysis, KPI validation, decision-support findings, recommendations and testing requirements.

SECTION 6 — RISKS

23. What risks affected or could affect your work during Week 6?

Risk 1: Cross-track integration unavailable. Cause: no Data Science counterpart. Effect: integration requirement remains incomplete. Probability 4/5; Impact 3/5. Mitigation: prepare a clear handoff and identify an integration point. Status: Open.

Risk 2: Over-interpreting observational associations. Cause: analytics shows relationships but not causation. Effect: misleading operational/model conclusions. Probability 3/5; Impact 4/5. Mitigation: clearly label associations and require validation.

24. Did any Week 5 risk change?

☒ Yes. The cross-track dependency became more concrete because the intended Data Science counterpart was unavailable. Recommended PM action: establish a named receiving counterpart before downstream testing.

25. Did any new risk emerge during Week 6?

☒ Yes. No available Data Science integration point means findings cannot yet be incorporated or validated downstream. Mitigation: prepare the handoff and document the pending integration.

SECTION 7 — ISSUES & BLOCKERS

26. Did an actual issue or blocker occur during Week 6?

☒ Yes
Issue: No available Data Science counterpart for intended integration.
Track affected: Data Analytics / intended Data Science integration.
Dependency affected: Cross-track handoff and downstream validation.
Impact: Integration deferred and no model/feature validation evidence.
Action: Document pending integration and prepare analytical handoff.
Status: Pending.

27. Is anything currently preventing your track from progressing?

☒ Yes — the intended cross-track integration cannot progress until a Data Science/ML counterpart is available.

SECTION 8 — DECISIONS

28. Did your track require a project decision during Week 6?

☒ Yes
Decision: Report Data Science integration as pending rather than completed.
Why: The questionnaire requires actual evidence and prohibits claiming uncompleted work.
Recommended/made decision: Report actual status as pending.
Workstreams affected: Data Analytics and intended Data Science integration.

29. Is any decision still outstanding?

☒ Yes
Decision required: Assignment/availability of a Data Science integration counterpart.
Consequence of delay: No confirmed integration evidence or downstream feature validation.

SECTION 9 — OUTPUTS & EVIDENCE

30. Significant Week 6 outputs

1. Advanced HealthConnect analysis — Completed.
2. KPI validation — Completed.
3. Lead Time × Reminder analysis — Completed.
4. Previous No-Show risk segmentation — Completed.
5. Distance × Reminder analysis — Completed/developed as advanced segmentation.
6. Decision-support insights and recommendations — Completed.
7. Data Science candidate-feature handoff content — Prepared, not integrated.
8. Week 7 testing requirements — Prepared.
9. Week 6 decision-support dashboard/page — Developed.

31. What evidence proves completion?

☒ Updated document
☒ Dataset/analysis
☒ Dashboard
☒ Documentation
☒ KPI calculations and analytical results.

32. What evidence proves actual integration?

☒ Not yet integrated. No downstream model, pipeline, joint output or review record exists.

SECTION 10 — PROJECT IMPACT

33. How did Week 6 contribute to the HealthConnect objective?

The analysis moved the project from describing appointment outcomes toward identifying actionable risk segments. It highlighted long booking lead times, repeated previous no-shows and longer distance as higher observed no-show segments, while showing lower observed no-show rates among patients receiving reminders. These findings can inform targeted appointment-management strategies and future predictive modelling.

34. What project-level capability/outcome did your work enable or improve?

☒ Better data/insight
☒ Better patient intervention
☒ Better operational workflow
☒ Better validation readiness
Explanation: The work produced detailed risk segmentation, decision-support insights and a clearer basis for targeted interventions and future testing.

35. Did your work change anything outside your own track?

☒ No. No confirmed downstream change occurred because Data Science integration was not completed.

SECTION 11 — WEEK 7 TESTING & REFINEMENT READINESS

36. What must your track complete before Week 7?

1. Finalise Week 6 decision-support dashboard.
2. Complete/record Data Science handoff when a counterpart is available.
3. Confirm analytical definitions and KPI calculations.
4. Finalise missing-value/data-quality notes.
5. Finalise Week 7 testing criteria.

37. What does your track need from other workstreams before Week 7?

Data Science: review of candidate features and, if applicable, model-feature testing results. Purpose: determine usefulness and avoid leakage. Status: Pending.

38. Is your current output ready to enter Week 7 testing/refinement?

☒ Conditionally
The analytics output is sufficiently developed for testing preparation, but cross-track validation remains pending.

39. What should be tested/validated in Week 7?

1. Stability of lead-time and previous-no-show patterns on new/held-out data.
2. Whether candidate features improve prediction without leakage.
3. Whether reminder status remains useful after accounting for other variables.
4. Operational usefulness of high-risk segments.
5. KPI consistency after refresh/transformation.
6. Effect of missing distance/waiting-time values.

40. Acceptance criteria

1. KPI totals/rates reconcile after refresh.
2. Key patterns remain reasonably stable on validation/new data.
3. Candidate features are available at prediction time and do not leak future information.
4. Predictive improvement is demonstrated using appropriate validation data.
5. Recommendations remain evidence-based and non-causal.

41. What could prevent successful Week 7 testing?

Potential constraint: unresolved Data Science integration and missing receiving-track validation. Impact: feature/model testing may be delayed. Mitigation: establish a Data Science integration point, complete handoff and agree validation criteria.

SECTION 12 — PM COORDINATION PRIORITIES

42. MOST IMPORTANT dependency

Data Science/ML receiving counterpart availability. It matters because the analytical output is prepared for downstream predictive use but has not been integrated. Control: assign a named counterpart and record the handoff/review.

43. MOST IMPORTANT risk

Using observational findings as causal or unvalidated features downstream. Mitigation: validate on appropriate data, document assumptions and check for leakage.

44. MOST IMPORTANT unresolved issue

Lack of an available Data Science counterpart for intended cross-track integration.

45. MOST IMPORTANT decision required

Confirm who will receive, review and potentially integrate the HealthConnect analytical findings into Data Science/no-show prediction work.

46. MOST IMPORTANT thing another track needs to know

The strongest observed patterns involved previous no-show history and booking lead time, with distance and reminder status providing additional segmentation value. These are candidate features for testing, not automatically validated predictive features.

47. MOST IMPORTANT thing needed from Project Management

A confirmed Data Science/ML integration point and clear handoff/validation process before downstream testing.

SECTION 13 — WEEK 6 INTEGRATION SUMMARY

Final Integration Summary

At the end of Week 5, our track had: an initial HealthConnect appointment dashboard with KPIs, visual analysis, insights and recommendations.

During Week 6, we improved/developed: deeper segmentation, KPI validation, cross-variable analysis, prioritised risk findings, decision-support recommendations, dashboard content and Week 7 testing requirements.

We integrated with: No cross-track integration occurred; Data Science was the intended receiving track.

We received: No cross-track input was received.

We provided: Prepared analytical findings and candidate features for potential Data Science use.

The actual integration activity was: Not yet started because no available Data Scientist/receiving track was identified.

The integration outcome was: Planned/pending, not completed.

As a result, the project/workstream changed by: No confirmed downstream change; the Analytics output was strengthened and prepared for future integration.

Evidence of the change: Week 6 analysis, KPI validation, dashboard/documentation and prepared handoff content. No downstream artefact exists yet.

Our current output status is: Produced and conditionally ready for downstream review/testing.

The main remaining dependency is: Data Science/ML receiving counterpart.

The main remaining risk is: Unvalidated downstream use and over-interpretation of observational findings.

The main remaining issue is: Cross-track integration not yet completed.

The main outstanding decision is: Assignment of a Data Science integration counterpart.

Our priority going into Week 7 is: Validate analytical stability, prepare downstream feature testing and complete the pending cross-track handoff when a receiving counterpart is available.